## BOE
Functional Tasks
Feature |  | Planning Phase | [6 empty] | Construction Phase | [6 empty] | Stabilization Phase
| Req. Definition | Prototype/Modeling | Review/ Usability/ Modify | Use Cases | Func. Specs | Technical Design | Design Review | Planning Total | Unit Test Cases | Test case creation | Test case execution | Database | Code Review | Unit Test | Const. Total | System Test Cases | System Test | Defect Resolution | Stabil. Total | Project Total Hours | Course notes
Back-end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 30
Project Setup | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 |  | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 30
Initial project setup | [7 empty] | 0 |  | 30 | 5 |  |  |  | 35 |  |  |  | 0 | 35 | Setting up configuration files, setting up version control, onboarding new developers as necessary, create high-level technical documentation
Security Updates | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | Add 2 security groups to active directory - Admin and User
[8 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Data Service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initial setup and creation | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | Create the project, create config files, figure out what methods you'll need
Development | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | Actual development of the service in C#
[8 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Workflow Service | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Initial setup and creation | [5 empty] | 4 |  | 4 | [6 empty] | 0 |  |  |  | 0 | 4 | Create the project, create config files, figure out what methods you'll need
Development | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | Actual development of the service in Workflow Foundation and C#
[8 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Diagnostics Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL Updates | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | Add 1 table which will hold generic log messages emitted by the services and mobile app
Service Development | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | Configure both services to connect to the diagnostic table from line 18, and add custom log messages to the services
[8 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Quality Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Business Clarification & Verification | [7 empty] | 5 | [6 empty] | 0 |  |  |  | 0 | 5 | optional - add hours for getting clarification from business people
End of Phase Reviews | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Approval/Signoffs | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Performance/Load Testing | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Migration/Build Process | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Mentoring | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Technical Support | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Test Planning | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
SIT Execution | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Testing Support | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Environment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Workstation setup | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | installing and configuring required software
Environment Set-up (QA and Prod) | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Data Loads/Extracts | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Code Builds and Deployments | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | hours for building and deploying releases
Project Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Mgmt | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Status Meetings | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Management Reserve | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Architecture Support and Mentoring | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Deployment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Doc. / Training Cheat Sheet | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | Hours for creating documentation
Training & KT | [7 empty] | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | hours for training business users on the application, using documentation created in line 43
Grand Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 30
Note on Q3: SShin: Includes Test Case Reviews = 5%-10%

## Assumptions
Base requirements off of the requirement specification document and the design specification for validation