## BOE
Functional Tasks
Feature |  |  |  | Construction Phase | [6 empty] | Testing, Management & Support
Registration Solution | Technical Design | Design Review | Planning Total | Unit Test Cases | Web | Component | Database | Unit Test | Code Review | Const. Total | Testing | Mgmt. | Support | Mgmt. Testing Total | Project Total Hours
Servlet and Database | 16 | 0 | 16 | 0 | 0 | 42 | 2 | 9 | 4 | 57 | 10 | 0 | 0 | 10 | 83
Initial repository setup, configuration files, documentation | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 15
Database setup, schema design, model creation | 2 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 6
Servlet Resources setup | 2 | 0 | 2 | 4 | 0 | 20 | 0 | 2 | 2 | 28 | 5 | 0 | 0 | 5 | 35
Servlet Services setup | 2 | 0 | 2 | 4 | 0 | 20 | 0 | 2 | 2 | 28 | 5 | 0 | 0 | 5 | 35
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Front End Development | 16 | 2 | 18 | 0 | 67 | 10 | 0 | 5 | 0 | 82 | 15 | 0 | 0 | 15 | 115
Initial setup | 4 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 6
Development | 10 | 2 | 12 | 0 | 40 | 5 | 0 | 5 | 0 | 50 | 10 | 0 | 0 | 10 | 72
UI UX Development | 2 | 0 | 2 | 0 | 25 | 5 | 0 | 0 | 0 | 30 | 5 | 0 | 0 | 5 | 37
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
|  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0
Grand Totals | 32 | 2 | 34 | 0 | 67 | 52 | 2 | 14 | 4 | 139 | 25 | 0 | 0 | 25 | 198
Notes:

## Sheet1
Weeks
Task | Total Hours | Working Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
Design | 1512 | 1520 | Weeks 1: 2; Weeks 2: 2; Weeks 3: 2; Weeks 4: 2; Weeks 5: 2; Weeks 6: 2; Weeks 7: 2; Weeks 8: 2; Weeks 9: 2; Weeks 10: 2; Weeks 11: 2; Weeks 12: 2; Weeks 13: 2; Weeks 14: 2; Weeks 15: 2; Weeks 16: 2; Weeks 17: 2; Weeks 18: 2; Weeks 19: 2
Development | 6460 | 6440 | Weeks 8: 9; Weeks 9: 9; Weeks 10: 9; Weeks 11: 9; Weeks 12: 9; Weeks 13: 9; Weeks 14: 9; Weeks 15: 9; Weeks 16: 9; Weeks 17: 10; Weeks 18: 10; Weeks 19: 10; Weeks 20: 10; Weeks 21: 10; Weeks 22: 10; Weeks 23: 10; Weeks 24: 10